## Internal Timeline
8 Week Implementation
Phase/Week | Group Owner | Objective | Due Date | Dependencies/Notes | Responsible | Status
Week 1: (enter date) | Career Services | Add Career Services Staff to Handshake and review their roles |  |  |  | Complete
| Career Services | Explore Self-Paced Training Videos |  |  |  | In Progress
| Career Services | Create Student and Employer Accounts linked to Career Services Accounts |  |  |  | Delayed
| IT | Review Tech Documentation |  |  |  | N/A
| IT | Student File Requirements
| IT | Coursework
| IT | Whitelisting
| IT | SSO
| Training | Handshake Orientation (ImplementationTeam/Employer Team)
| Training | Account Set-Up (ImplementationTeam/Employer Team)
| Training | Importer Training (Sherry, Abbie, ITS)
Week 2: | Career Services | Configure details tab of school settings
| Career Services | Order Handshake Chair
| Career Services | Download student & employer engagement metrics from previous system
| Career Services | Import past system metrics in the importer
| Career Services | Configure Branding page for Career Center
| IT | Whitelist Handshake IP & Domains
| IT | Compete the importer training to gain access
| Training | Complete Importer Training
| Training | PCC Training: Orientation/Account Set-Up
Week 3: | Career Services | Configure Employer Approval Settings
| Career Services | Configure Interview Settings: Including interview templates, timelines, seasons and preferences
| Career Services | Interview Preferences
| Career Services | Decide whether to activate/make viewable to employers # rooms available
| Career Services | Interview Templates
| Career Services | Update all to our 8:30am start-time/4:30pm end time
| Career Services | Interview Timelines
| Career Services | Interview Seasons
| Career Services | Configure Event Settings
| Career Services | Develop "Event Agreement" Survey to connect to Event Registration Form
| Career Services | Update the Tabling/info Session web page to proactively address the Handshake "format" language
| Career Services | Decide on On-Campus Employer Model
| Career Services | Determine set-up/import needs for on-campus employer contacts
| Career Services | Provide instructions to Angi for on-campus employer communication
| Career Services | Import Employer Contact File
| Career Services | Determine how far back to import contacts
| Career Services | Review Contact List
| Career Services | Clean Data for Import
| Career Services | Notify Symplicity
| Career Services | Communications/Marketing Projects
| Career Services | Constituent Communications Drafted (employers, students, university stakeholders faculty, in-home employers)
| Career Services | Student flyer for Orientation
| Career Services | Images for Handshake branding pages (University, PCC)
| Career Services | Images for HaH page (square, banner)
| Career Services | Determine HaH Web update process
| Career Services | Prepare HaH update content
| Training | Complete Employers Training
| Training | Complete Interview Schedules Training
| Training | Compelte Interview Schedules Advanced Training
| Training | Complete Jobs Training
| Training | Complete Jobs Advance Training
Week 4: | Career Services | Send out Student document retreival notice?
| Career Services | Send out student internship registration notice - when to enter data in which system
| Career Services | Training & collateral material work
| Career Services | Transfer Orientation (5/9) - update image with new Branding
| Career Services | CLA (5/15) see Document & collateral Updates
| Career Services | PCC Staff Training phase 2 sent out (application practice)
| IT/Carer Services | Meeting to confirm criteria logc; re-set timelines
| Career Services | Criteria for student data pull sent to ITS
| IT | Importer: Upload Student Coursework Data
| IT | Complete: SSO Testing
Week 5: | Career Services | Complete Program Key Naming Conventions and send to ITS (major mapping project)
| Career Services | Document Employer/Job Approval Procedures for Handshake
| Career Services | Send out Marketing Email to Employers and Stakeholders prior to the official Handshake Invite
| Career Services | Meeting with Student Employment to confirm process needs for system set-up
| Career Services | Collateral Materials:
| Career Services | Review employer/student webpages and content update needs
| Career Services | Prepare HaH content for update
Weeks 6&7: | IT | Complete: Format Your Student file
Catch Up | IT | Importer: Upload Student Data
| Career Services | Create Employer process documents for job approvals, interviews and event requests
| Career Services | Configure Settings: Mapping Majors
| Career Services | Add employer and student resume review labels as needed
| Career Services | Add (send instructions for adding) mass emails to be used for Experiences, Employers - Parking etc.
| Career Service | Create Resume Review Process
| Career Services | Confirm any Employer Module elements that need review/completion (jobs, interviews, events, etc.)
| Career Services | Make updates to Essential Employer Web Pages
Branding - Confirm Career Services/PCC pages are all branded correctly (see Above)
| Career Services | Collateral Materials:
Orientation Post Card
| Career Services | Begin manually entering SU and FA internship records
Week 8: | Career Services | Import employer contacts added after 5/30
Invite Employer contacts to connect
| Career Services | Configure Experiences
| IT | Configure Automated Sync
| Career Services | Update Staff accounts for SSO protocols?
| Training | Complete Surveys Training
| Training | Complete Events & Career Fairs Training
| Career Services | Complete Resume Review process and test
| Career Services | Complete Experiential Education - Adding Experiences process and test
| Training | Complete Expereinces Training (optional)
Week 9: | Career Services | Fill out Form for Handshake to create Student Launch email & update Student User Email in System Settings
| Career Services | Develop promotional Handshake materials
| Career Services | Configure University Student Account Request Message
| Career Services | Configure payment options
| Career Services | Verify school settings prior to Launch
| Career Services | Create student process documents - account approvals, resume review etc.
| Career Services | Branding:
| Career Services | Configure Kiosk/Card Swipe
| Career Services | Upate website info, HAH current system announcements, new system Pins/Articles
| Training | Register for Upcoming or Previous Webinars
| Training | Reporting Training
| Career Services | Configure First Destination Survey
| Career Services | Configure Settings: Appointment Types/Categories
| Training | First Destination Survey Training
| Training | Appointments Training
| Training | Advanced Appointments Training
Week 10: | Career Services | Launch to Students
Configure Manually or Import Buildings and Rooms
Import: Additional Historical Upload Data for Notes, Attendees, Events, and Appontmeints
Week 11: | Career Services | Pull historical data from current system and save to shared drive
Check for new documents uploaded to HireaHawk - review and approve or send email to upload into the new system July 1
Check for new pending student account requests - email to create new in Handshake July 1 - do not approve?
Check for any new employer accounts/jobs and email to create accounts in Handshake??

## Communication Plan
Date | Audience | Communication Label | Delivery Channel | Sender / Lead | Key Message(s) | Responsible | Progress
Week of 5/7 | Students with Accounts in HaH | Pre-Launch Transition Notification | email |  | HaH transitioning in June; retreive documents
Week of 5/7 | HaH student/alumni users | Pre-Launch Transtion Notification | Notice posted in HaH |  | HaH transitioning in June; retreive documents
Week of 5/7 | Alumni with Accounts in HaH | Pre-Launch Transition Notification | email |  | HaH transitioning in June; retreive documents
Week of 5/7 | Student Employment Employers (off-campus ) | Pre-Launch Transition Notification | email |  | HaH transition; retrieve postings; look for invite
Week of 5/7 | Student Employment Employers (on-campus) | Pre-Launch Transition Notification | email |  | HaH transition; retrieve postings; look for invite
Week of 5/7 | Student Employment Employers (home-based) | Pre-Launch Transition Notification | email |  | HaH Transition; no longer accepting home-based positions
Week of 5/7 | PCC Employers | Pre-Launch Transition Notification | email |  | HaH transition; retrieve postings; look for invite
| Students with Accounts in HaH | Pre-Launch Document Download Reminder | email |  | Reminder to retrieve documents
| Alumni with Accounts in HaH | Pre-Launch Document Download Reminder | email |  | Reminder to retrieve documents
| University Partners | Pre-Launch Transition Notification | email |  | HaH transition
Week of 6/4 | Student Employment Employers (off-campus ) | Employer Launch | email |  | Handshake launched; should receive invite to create account
Week of 6/4 | Student Employment Employers (on-campus) | Employer Launch | email |  | Handshake launched; should receive invite to create account
Week of 6/4 | PCC Employers | Employer Launch | email |  | Handshake launched; should receive invite to create account

## Training Needs
Key Group(s) | Training Component | Key Liaison / Contributor to | Training Delivery Method | Individual / Group Responsible for Creating & Delivering the Training | Training Length, Date & | Timing
(who) | (what) | Training Group | (how) |  | Next Step Assignments
(point of contact)
PCC Staff | • Philosophy & Overall Process • Initial Functionality • Account Set-Up |  |  |  | • 45 - 60 minutes (non-consecutive) • Self-paced; goal of completion by 5/7
PCC Staff | Q&A & Real Time Demos |  |  |  | • 45 - 60 minutes • 5/16/18 Noon-1pm
PCC Staff | • Role Based Training (see below) • Applied Practice
PCC - Career Advisors | • Student view - Create profile, upload document, apply for job •Career Services View - Review/approve document; look up a student/log-in as them; look up an employer • Employer view - review an applicant, invite to interview. • Optional - if supervise students or want to see employer full picture complete Employer Team tasks
PCC - Employer Team | • Employer view - Create job/interview schedule, review applicants, invite to interview •Career Services View - Review/approve job posting and interview schedule, dowload schedule/packet; approve employer • Student - apply for job, sign up for interview
PCC - Experiential Ed Team
PCC - Peer Advisors | • Philosophy & Overall Process • Initial Functionality • Account Set-Up |  |  |  | • 45 - 60 minutes (non-consecutive) • Self-paced; goal of completion by 5/7
PCC - Peer Advisors | • Role Based Training • Applied Practice (same as career advisors?)
PCC - Peer Advisors
Student Employment
Engineering

## Work Groups
Stakeholders/Audience | Core Team Liaison | Role/Purpose | Handshake Module | Related Resources | Input Requested | Input Provided | Questions to Follow-Up On
Core Team |  | The role of the core team is to provide overall project managent for implementation of handshake. Members will advise on the key decisions needed for handshake system set-up and tultimate launch. Primary activities will be coordinating with ITS and all work groups to get teh system set-up, as well as overseeing the communication and training plan. |  |  | • Import • Single sign-on • Payments • Calendar integration • RSS Feeds • System Set-Up • Data Reporting
Student Employment: POC NAME |  | Student employment plays a crucial role for University of Iowa students looking to increase their financial resources as well as to develop skills for future employment. As we convert to Handshake, we want to ensure that the system set-up options selected work well for process workflows, and provide students access to beneficial opportunities with a reasonable assurance of student safety. | Campus Employment | • On Campus Employment Guide: Steps for how to set-up up the campus employment module • On Campus Employment Set-Up On-line Training: Online training for setting up on-campus employer accounts (note this will require creating an account in Handshake University to view). | • How will we set-up On Campus Employment – Division Model or Company Model (see On Campus Employment Guide for implications of each). • Work Study Set-Up – Do we want to configure the system so that only students who are eligible for work-study will be able to see work-study jobs? Do we want to import work study eligibility? • How will community postings be handled? | Campus Employment - Company Model; Work Study - leaning toward yes, Cindy double-checking on FERPA and other considerations; Community Postiongs - leaning towards directing to other sites, Cindy is checking on this.
Experiential Education Team POC: NAME |  | Multiple offices on campus capture reporting of student experiences through HireaHawk. As we transition to Handshake, we need to determine what changes in process may take place, and the implications for various stakeholders who track experiences. We will need to update our process and timeline for students registering internship experiences and CPT. | Experiences | • Help Center Articles: https://support.joinhandshake.com/hc/en-us/sections/204201938-Experiences | • Input on OISS Accounts • Implications for stakeholder groups (CSIL, Athletics, etc.) • Recommendations on timelines for registering experiences • Process Implications
Academic Programs/Course Instructors POC: NAME |  | PCC offers over 30 different courses, many of which integrate assignments related to Career Center services and HireaHawk, as do man departmental courses. As we make the transition to Handshake, we want to ensure that we understand the ways course instructors integrate HaH into classes and the impact of this change. | Faculty Account Set-up, Student Account | • Handshake LMS Training – Career Counselor Path https://support.joinhandshake.com/hc/en-us/articles/115010311488-Career-Services-Training-Courses-by-Role • Help Center Articles: https://support.joinhandshake.com/hc/en-us/categories/202711128-Student-Alumni | • Course Uses and timeline of needed capabilities (e.g. access in week 1 vs. week 4) • Resources in need of updating/creation to support course • Input on Faculty account set-up
Employer Relations Team POC: NAME |  | Employers and students are the primary users of HireaHawk. This group will work on all the considerations needed to ensure our employers transition to handshake relatively seamlessly. | Employers, Jobs, Event & Career Fairs, Interview Schedules | • Help Center Articles: https://support.joinhandshake.com/hc/en-us/categories/202707317-Career-Services • Handshake LMS Training – Employer Relations/Marketing Path https://support.joinhandshake.com/hc/en-us/articles/115010311488-Career-Services-Training-Courses-by-Role | • Considerations Employer Account Set-Up • Job Posting Set-up & protocols • Interview Schedule Setting Set-Up & protocols • Event Setting • Creation of upcoming events/career fairs • General timelines for OCR/Event
Marketing POC: NAME |  | The transition to Handshake will require a comprehensive communications and marketing plan along with branding and collateral materials. This group wil help to ensure all elements are ready for various stages of implementation and roll-out. |  | • Handshake Help Center (Including student launch tool kit): https://support.joinhandshake.com/hc/en-us/sections/206599388-Marketing • Image Size Guide: https://support.joinhandshake.com/hc/en-us/articles/219132827-School-Settings-Handshake-Image-Size-Guide • Email invite Examples: https://support.joinhandshake.com/hc/en-us/articles/115007135747-Invite-Email-Examples | • Branding and content for system set-up, including logos • Creation of a Backgrounder document with key messages to be used throughout the transition • Updates to PCC collateral materials as needed • Communication plan/messages for each audience at each phase of launch
Students/Alumni POC: NAME |  | Students/alumni are our primary users of HireaHawk and are supported in their use of it through a variety of modes - online resources, career guide, Career Advisors, Peer Advisors, etc. This group will help to identifiy key considerations and needs as they relate to rolling Handshake out to our students. | Student/Alumni Profiles, Resources | • Help Center Articles: https://support.joinhandshake.com/hc/en-us/categories/202711128-Student-Alumni | • Considerations for the resume review process – 1) Peers; 2)making sure Engineering can filter on and view the resumes they need to review • Updates needed to student resources and where they should be housed (PCC website or in Handshake Resources section) • Input on alumni account set-up • Input on training needs for Peers/Peer involvement in implementation • Input on involvement of academic advising/departmental contacts • Input on Career Advisor/PCC Staff Training • Implications for Transfer/New Student Orientation • Input on Major Mapping

## Document & Collateral Updates
Team Responsible | Item | Stage 1 (by go live) or 2 (after go live) | Deadline/Due Date for Updates | Status
Experiential Education | Student Internship Manual | Stage 1
Experiential Education | Employer Manual | Stage 1
Experiential Education | Zero Credit Hour ICON Courses | Stage 1
Experiential Education | Academic Internship ICON Courses | Stage 1
Experiential Education | Leadership Certificate/TWC -other internship related ICON Courses
Experiential Education | Course Catalog | Stage 2 - add info/link in course catalog to internship reg. process - link to Handshake to add experience for a more direct link to registration?
Experiential Education | Handouts - advisor resources | Gain Experience, full page sheet with registration options
Experiential Education | Any presentation powerpoints?
Experiential Education | Website -
Evaluations - Student and Employer
Mass Email Templates
Website Announcements
Experiential Education | Audit all UI departmental websites (Tippie, Psych, Comm. Etc. to make sure the instructions for registering internships are up to date - OISS Site as well- CPT info.
Marketing | Career Guide | Stage 2 - For regular fall distribution
Employer Relations | Employer Guide
website - update text about what can be posted for student employment positions, update Policies document if needed and instructions for posting
- links for logging in and previewing system
Fairs and Events
Student Alumni/Core
Stage 1
Academic Programs/CLA |  | Stage 1
Stage 2
Stage 2
Stage 2